## Sheet1
System Name: Mako Real Estate Management System
Members:
Alon, Mike Francis
Fernandez, Cg
Baluntang, Rendolf
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Functional Requirements | Alon, Fernandez, Baluntang | 2024-08-28 |  | Done
1.1 Modeling (Conceptual) | Alon, Fernandez, Baluntang | 2024-08-28 |  | Done
1.2 Modeling (Logical) | Fernandez | 2024-08-28 |  | Done
User login | Fernandez | 2024-09-20 |  | In- Progress
Account Registration | Fernandez |  |  | In- Progress
Permission | Fernandez |  |  | In- Progress
Roles | Fernandez |  |  | In- Progress
Landing page | Fernandez |  |  | In- Progress
User profile | Alon | 2024-09-25 |  | In- Progress
Property listing | Alon | 2024-09-25 |  | In- Progress
Change role | Alon